## Course Management
| Office Hours System | Product and Sprint Backlog with Summaries |  |  | Spring 2016
Software Engineering
|  | Item | Last Update
|  | Main Backlog Items: | 2016-04-26
|  | Main Backlog Priority | 2016-04-26
|  | Sprint Logs: | 2016-04-28
|  | Status Updated: | 2016-04-28
Sprints
ID | Sprint Title | Start Date | End Date | Status | Notes
1 | Sprint 1 | 2016-03-22 | 2016-04-05 | Completed
2 | Sprint 2 | 2016-04-05 | 2016-04-19 | Completed | Changed end date and subsequent end dates starting at sprint 2 due to unexpected teammember obsticles
3 | Sprint 3 | 2016-04-19 | 2016-04-26 | Completed
4 | Sprint 4 | 2016-04-26 | 2016-05-03 | Completed
| Product Backlog | Top Level Features | Sprint 1 | Sprint 2 | Sprint3 | Sprint 4
ID | Feature | Priority (high = 1 / 5 = low) | 1: Status | 2: Status | 3: Status | 4: Status
0 | Allow user to make appointments | 1 |  | In Progress (75%) | In Progress | In Progress
1 | Email ICS Calendar invitation | 2 |  | In Progress (75%) | Done | Done
2 | Retrieve Faculty list from Café | 2 |  | In Progress | In Progress (70%) | Done
3 | Retrieve faculty office hours from Café | 1 |  | In Progress | In Progress (70%) | Done
4 | Display calendar on webpage | 3 |  | In Progress | Done | Done
5 | Authenticate / Identify user | 3 |  | Waiting | Done | Done
6 | Define Appointment database schema | 1 |  | Done | Done | Done
7 | General Web UI | 3 |  | In Progress | Done | Done
8 | Integration of Components (added 4-26-16) | 1 |  | Waiting | In Progress (10%) | In Progress
9 | * General Documentation * | *
10
11
12
Sprint 1 Backlog (Done)
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Each member creates his own set of perceived project features and subtasks. | * | All | Completed
2 | Each member estimates priority and difficulty of main features and subtasks | * | All | Completed
3 | Each member learns unknown technologies  C#, ASP.NET, SQL, Git | * | All | Completed
4 | Create Preliminary Product Backlog and System Diagrams | * | All | Completed
5
6
7
Sprint 2 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Define what new databases we need for the program | 6 | Naif | Done
2 | Define overall database structure, accounting for what data is available and what data we need from the Cafe system. | 6 | Naif | 80% | Faculty, terms, office hours from café. Done | Pushed to sprint 3
3 | Create any new databases and/or tables in microsoft sql on our project side (ie. not in cafe) | 6 | Naif | Done | Created "appointments" Done
4 | Test cases: What is the form of the data for each record; How is it validated | 6 | Naif | Done
5 | Define the format of the ICS file/files we need for the project | 1 | Jimmy | Done
6 | Send a calendar file | 1 | Jimmy | Done | Code compiles; waiting on SMTP IP
7 | Validate working with Gannon outlook | 1 | Jimmy | Done | Anticipated, Waiting on SMPT IP
8 | Validate accept/decline uses | 1 | Jimmy | Done | Anticipated, waiting on SMTP IP
9 | Define best user flow for sending receiving | 1 | Jimmy | 60% |  | Pushed to sprint 3
10 | What data do we need from user / prof to send receive invites | 1 | Jimmy | 60% | Class has most data | Pushed to sprint 3
11 | Create Basic calendar in C# / ASP.NET that can be used/migrated to a webapp in those technologies | 4 | Andrew | Done
12 | Investigate its ability to be extended to include visual indication of: Professors’ Office Hours; Current appointments | 4 | Andrew | 75% |  | Task removed from backlog
13 | Retrieve data from Cafe system | 2, 3 | Tom | Done | Still writing test cases for all data
14 | Define the interface between our system (dbs, controller logic) and the cafe system (specifically, its data) | 2 | Tom | 50%
15
16
Sprint 3 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Migrate Appointment DB to webapp server (LINQ) | 6 | Naif, tom | 30%; pushed to Sprint 4 | unable to get into the database
2 | Process data from welcome page to calendar page | 4,6 | Andrew | Done
3 | drop down; email | 4,6 | Andrew | Done
4 | Integrate calendar/email with webapp | 1,6,4 | Jimmy, Andrew | 50%; Moved to Sprint 4
5 | create interface/methods to retrieve data from UI/logic | 1,6,4 | Jimmy | Done
6 | logic on data in controller for sending ics | 1,6,4 | Jimmy, Tom | Done
7 | connecting to UI |  | Andrew, Jimmy | Moved to Sprint 4
8 | Populate proffessors drop down with data from Café | 4,7 | Andrew, Naif | On hold | unable to get into the database | Duffin?
9 | (Last, First) |  | Andrew, Naif | On hold | unable to get into the database | Duffin?
10 | Dynamically link the static office hours table to café data | 4,7 | Andrew, Tom | On hold | unable to get into the database
11 | Dynamically link the dynamic office hours radio buttons with café data | 4,7 | Andrew, Tom | On hold | unable to get into the database
12 | Create appoint records in appointment database |  | Naif | Done
13 | Create a login/user table(s) | 5 | Tom | Done
14 | hashing/security for passwords | 5 | Naif, Tom | Done
15 | change landing page to login / sign up page | 5 | Jimmy, Andrew | Done
16 | validation of Gannon email (regex) | 5 | Tom, Andrew | Done
15 (3.14) | Define the interface between our system (dbs, controller logic) and the cafe system (specifically, its data) | 2 | Tom | Done; Abandoned
16 (3.9) | Define best user flow for sending receiving | 1 | Jimmy | Done
17 (3.10) | What data do we need from user / prof to send receive invites | 1 | Jimmy | Done | Class has most data
18 (3.2) | Define overall database structure, accounting for what data is available and what data we need from the Cafe system. | 6 | Naif | Done | Faculty, terms, office hours from café. Done
19 | Create different messages for student professor in ics email | 1 | Jimmy | Done
Sprint 4 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Complete Team Report | * | Tom, Jimmy | Done | Sunday
2 | Integrate ics/email with webapp | 8, 1 | Jimmy | 75% |  | Code to send email is complete, in project, and the methods created. Next is getting data to the method; some data is not in ready form
3 | Integrate CAFÉ data and login into webapp | 8 | Tom | Incomplete |  | Code written; no time to integrate
4 | Integrate Appointment database with webapp | 8 | Naif | Incomplete
5 - 4.8 | Populate proffessors drop down with data from Café | 4,7 | Andrew | Done
6 - 4.9 | (Last, First) | 4,8 | Andrew | Done
7 - 4.1 | Dynamically link the static office hours table to café data | 4,7 | Andrew, Tom | Done
8 - 4.11 | Dynamically link the dynamic office hours radio buttons with café data | 4,7 | Andrew, Tom | Done
9 | Schedule stakeholder meeting | * | All, Jimmy | Done
10 - 4.1 | Migrate Appointment DB to webapp server (LINQ) | 6 | Jimmy, naif | Done
11 | Create landing page after submission in GUI | 0 | Andrew, Jimmy | Done
Sprint 5 Backlog (Future)
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Integration code for account database (account.aspx.cs) |  |  | Feature
2 | Verification code on submit of credentials on welcome page (query account database) |  |  | Feature
3 | Integration of appointment database code (calendar.aspx.cs) |  |  | Feature
4 | In updateAvailableHoursTable(), check for appointments in appointment database, disable (or delete) timeslots that have already been requested. |  |  | Feature
5 | Table disappears when a time is selected. |  |  | Bug
6 | DateTime object to pass to the ICS sender (MM/DD/YYYY from calendar, and HOUR:MINUTE from radio button selection; with proper formatting from a function) |  |  | Bug | Code started on "server_sprint4", needs completed
7 | Professor’s email producing when passed to ICS sender? |  |  | Bug