## Course Management
| Office Hours System | Product and Sprint Backlog with Summaries |  |  | Spring 2016
Software Engineering
|  | Item | Last Update
|  | Main Backlog Items: | 2016-04-03
|  | Main Backlog Priority | 2016-04-03
|  | Sprint Logs: | 2016-04-07
Sprints
ID | Sprint Title | Start Date | End Date | Status | Notes
1 | Sprint 1 | 2016-03-22 | 2016-04-05 | Completed
2 | Sprint 2 | 2016-04-05 | 2016-04-12 | In Progress
3 | Sprint 3 | 2016-04-12 | 2016-04-19
4 | Sprint 4 | 2016-04-19 | 2016-04-26
5 | Sprint 5 | 2016-04-26 | 2016-04-30
| Product Backlog | Top Level Features | Sprint 1 | Sprint 2 | Sprint3 | Sprint 4
ID | Feature | Priority (high = 1 / 5 = low) | 1: Status | 2: Status | 3: Status | 4: Status
0 | Allow user to make appointments | 1 |  | In Progress
1 | Email ICS Calendar invitation | 2 |  | In Progress
2 | Retrieve Faculty list from Café | 2 |  | In Progress
3 | Retrieve faculty office hours from Café | 1 |  | In Progress
4 | Display calendar on webpage | 3 |  | In Progress
5 | Authenticate / Identify user | 4 |  | In Progress
6 | Define Appointment database schema | 1 |  | In Progress
7 | General Web UI | 3 |  | In Progress
8
9
10
11
12
Sprint 1 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Each member creates his own set of perceived project features and subtasks. | * | All | Completed
2 | Each member estimates priority and difficulty of main features and subtasks | * | All | Completed
3 | Each member learns unknown technologies  C#, ASP.NET, SQL, Git | * | All | Completed
4 | Create Preliminary Product Backlog and System Diagrams | * | All | Completed
5
6
7
Sprint 2 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1 | Define what new databases we need for the program | 6 | Naif | In Progress
2 | Define overall database structure, accounting for what data is available and what data we need from the Cafe system. | 6 | Naif | In Progress
3 | Create any new databases and/or tables in microsoft sql on our project side (ie. not in cafe) | 6 | Naif | In Progress
4 | Test cases: What is the form of the data for each record; How is it validated | 6 | Naif | In Progress
5 | Define the format of the ICS file/files we need for the project | 1 | Jimmy | In Progress
6 | Send a calendar file | 1 | Jimmy | In Progress
7 | Validate working with Gannon outlook | 1 | Jimmy | In Progress
8 | Validate accept/decline uses | 1 | Jimmy | In Progress
9 | Define best user flow for sending receiving | 1 | Jimmy | In Progress
10 | What data do we need from user / prof to send receive invites | 1 | Jimmy | In Progress
11 | Create Basic calendar in C# / ASP.NET that can be used/migrated to a webapp in those technologies | 4 | Andrew | In Progress
12 | Investigate its ability to be extended to include visual indication of: Professors’ Office Hours; Current appointments | 4 | Andrew | In Progress
13 | Retrieve data from Cafe system | 2 | Tom | In Progress
14 | Define the interface between our system (dbs, controller logic) and the cafe system (specifically, its data) | 2 | Tom | In Progress
15
16
Sprint 3 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1
2
3
4
5
6
7
Sprint 4 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1
2
3
4
5
Sprint 5 Backlog
ID | Subtask | Main Feature ID | Owned by | Current Status | Notes | Description of Incomplete
1
2
3
4
5